## Sheet1
Plan_CIDPID | Plan_Name | Plan_StartDate | Plan_EndDate | Program_Name | Program_Department | Program_Section | Program_NeedsPriorities | Program_Strategies | Program_Objectives | Program_Outcomes | Program_Remarks | Subprogram_Name | Subprogram_KeyOutcome | Subprogram_KPI | Subprogram_Baseline | Subprogram_Yr1Targets | Subprogram_Yr2Targets | Subprogram_Yr3Targets | Subprogram_Yr4Targets | Subprogram_Yr5Targets | Subprogram_Yr1Budget | Subprogram_Yr2Budget | Subprogram_Yr3Budget | Subprogram_Yr4Budget | Subprogram_Yr5Budget | Subprogram_TotalBudget | Subprogram_Remarks | Workplan_Name | Workplan_FinancialYear | Workplan_TotalBudget | Project_Name | Project_Category | Project_Cost | Milestone_Name | Milestone_DueDate | Activity_Name | Activity_StartDate | Activity_EndDate | Activity_BudgetAllocated
NAIROBI-2024-2029 | Nairobi Urban Health Strategic Plan | 2024-07-01 | 2029-06-30 | Urban Sanitation & Hygiene | Public Health | Environmental Health | High prevalence of waterborne diseases in informal settlements; inadequate waste management. | Implement community-led sanitation and waste management programs | Reduced incidence of waterborne diseases; Improved waste disposal rates | A cleaner and healthier urban environment with sustainable waste management. | Focus on public-private partnerships for waste collection services. | Kibera Sanitation and Waste Management | Improved sanitation and waste management in Kibera slums | Number of households with access to improved sanitation | 2000 | 2500 | 3000 | 3500 | 4000 | 500000 | 750000 | 1000000 | 1250000 | 1500000 | 5000000 | 9500000 | Phased implementation over 5 years. | FY 2024/2025 Kibera Health Workplan | 2024/2025 | 5000000 | Kibera Community Health Center Construction | Urban Infrastructure | 10000000 | Foundation Laid | 2024-11-30 | Site preparation and clearing | 2024-07-01 | 2024-08-31 | 1000000
NAIROBI-2024-2029 | Nairobi Urban Health Strategic Plan | 2024-07-01 | 2029-06-30 | Urban Sanitation & Hygiene | Public Health | Environmental Health | High prevalence of waterborne diseases in informal settlements; inadequate waste management. | Implement community-led sanitation and waste management programs | Reduced incidence of waterborne diseases; Improved waste disposal rates | A cleaner and healthier urban environment with sustainable waste management. | Focus on public-private partnerships for waste collection services. | Kibera Sanitation and Waste Management | Improved sanitation and waste management in Kibera slums | Number of households with access to improved sanitation | 2000 | 2500 | 3000 | 3500 | 4000 | 500000 | 750000 | 1000000 | 1250000 | 1500000 | 5000000 | 9500000 | Phased implementation over 5 years. | FY 2024/2025 Kibera Health Workplan | 2024/2025 | 5000000 | Kibera Community Health Center Construction | Urban Infrastructure | 10000000 | Center Inauguration | 2025-06-30 | Construct and equip the health center | 2024-11-01 | 2025-05-31 | 5000000
NAIROBI-2024-2029 | Nairobi Urban Health Strategic Plan | 2024-07-01 | 2029-06-30 | Maternal & Child Health | Public Health | Community Health | High maternal and infant mortality rates in low-income areas. | Enhance access to quality maternal and child health services | Reduced maternal mortality and increased immunization coverage | Healthier mothers and children in underserved communities. | Partnerships with local clinics and NGOs for training and outreach. | Community Maternal Health Outreach | Increased skilled birth attendance rates | Skilled birth attendance rate (%) | 70 | 75 | 80 | 85 | 90 | 1000000 | 1200000 | 1500000 | 1800000 | 2000000 | 7500000 | 14000000 | Community health workers training and deployment. | FY 2024/2025 Maternal Health Workplan | 2024/2025 | 3000000 | Mobile Clinic Deployment Project | Public Health Initiative | 5000000 | Initial Mobile Clinic Deployment | 2024-10-31 | Procure mobile clinic vehicles | 2024-07-15 | 2024-09-30 | 2000000
NAIROBI-2024-2029 | Nairobi Urban Health Strategic Plan | 2024-07-01 | 2029-06-30 | Maternal & Child Health | Public Health | Community Health | High maternal and infant mortality rates in low-income areas. | Enhance access to quality maternal and child health services | Reduced maternal mortality and increased immunization coverage | Healthier mothers and children in underserved communities. | Partnerships with local clinics and NGOs for training and outreach. | Community Maternal Health Outreach | Increased skilled birth attendance rates | Skilled birth attendance rate (%) | 70 | 75 | 80 | 85 | 90 | 1000000 | 1200000 | 1500000 | 1800000 | 2000000 | 7500000 | 14000000 | Community health workers training and deployment. | FY 2024/2025 Maternal Health Workplan | 2024/2025 | 3000000 | Mobile Clinic Deployment Project | Public Health Initiative | 5000000 | First 500 patients served | 2025-03-31 | Train community health workers | 2024-08-01 | 2024-09-15 | 500000
NAIROBI-2024-2029 | Nairobi Urban Health Strategic Plan | 2024-07-01 | 2029-06-30 | Maternal & Child Health | Public Health | Community Health | High maternal and infant mortality rates in low-income areas. | Enhance access to quality maternal and child health services | Reduced maternal mortality and increased immunization coverage | Healthier mothers and children in underserved communities. | Partnerships with local clinics and NGOs for training and outreach. | Community Maternal Health Outreach | Increased skilled birth attendance rates | Skilled birth attendance rate (%) | 70 | 75 | 80 | 85 | 90 | 1000000 | 1200000 | 1500000 | 1800000 | 2000000 | 7500000 | 14000000 | Community health workers training and deployment. | FY 2024/2025 Maternal Health Workplan | 2024/2025 | 3000000 | Mobile Clinic Deployment Project | Public Health Initiative | 5000000 | First 500 patients served | 2025-03-31 | Launch awareness campaigns | 2024-10-01 | 2024-11-30 | 300000
SS