## Sheet1
Project ID | Project Name | Department | Strategic Objective (CIDP Pillar) | Budget (KSh.) | Paid Out (KSh.) | Absorption Rate (%) | Start Date | End Date | Sub-County Distribution | GPS Coordinates (Approximate) | Status | Project Manager
AGR-1 | Tractor Hire Subsidy Rollout (Phase II) | 2 | Food Security (Pillar I) | 12000000 | 11500000 | 0.958 | 2023-01-01 | 2024-06-30 | Kitui East | -1.135, 38.450 | Completed | Mr. Kyalo Kimani
AGR-2 | Matinyani Certified Seeds & Training | 2 | Food Security (Pillar I) | 15000000 |  | 0.08 | 2024-07-01 | 2025-06-30 | Kitui West | -1.305, 37.690 | At Risk | Ms. Stella Mwende
AGR-3 | Countywide Livestock Vaccination Drive | 2 | Food Security (Pillar I) | 8500000 | 8450000 | 0.994 | 2022-11-01 | 2023-04-30 | Mwingi West | -1.020, 37.800 | Closed | Dr. Purity Nzomo
WTR-1 | Kwa Vonza Earth Dam Construction | 12 | Water Access (Pillar II) | 50000000 | 48500000 | 0.97 | 2022-10-01 | 2024-03-31 | Kitui Rural | -1.352, 37.965 | Completed | Eng. Mutua Nzioka
WTR-2 | Athi Ward Borehole Equipping | 12 | Water Access (Pillar II) | 30000000 | 28000000 | 0.933 | 2023-05-15 | 2025-06-30 | Kitui South | -2.050, 38.300 | Delayed | Eng. Paul Katana
WTR-3 | Mwingi Town Water Pipeline Extension | 12 | Water Access (Pillar II) | 65000000 | 32500000 | 0.5 | 2024-02-01 | 2026-01-30 | Mwingi Central | -0.945, 38.070 | In Progress | Eng. Rose Mutisya
HCS-1 | Kyuso Health Centre Level IV Upgrade | 1 | Healthcare (Pillar III) | 120000000 | 75000000 | 0.625 | 2022-07-01 | 2025-09-30 | Mwingi North | -0.650, 38.410 | In Progress | Dr. Janet Muli
HCS-2 | Community Health Volunteer Kits Procurement | 1 | Healthcare (Pillar III) | 7500000 | 7500000 | 1 | 2023-08-01 | 2024-01-31 | Kitui Central | -1.366, 38.012 | Completed | Ms. Carol Musyoka
HCS-3 | Mutomo Hospital Mortuary Renovation | 1 | Healthcare (Pillar III) | 10000000 | 1000000 | 0.1 | 2024-05-01 | 2025-03-30 | Kitui South | -1.880, 38.280 | Not Started | Mr. Julius Kithu
TCI-1 | Kitui Town Market Sheds Renovation | 14 | Aggregation & Industrial Parks (Pillar IV) | 28000000 | 5500000 | 0.196 | 2024-01-01 | 2025-12-31 | Kitui Central | -1.370, 38.010 | Stalled | Mr. Benjamin Kimanthi
TCI-2 | Youth Enterprise Fund Disbursement (Phase 2) | 14 | Aggregation & Industrial Parks (Pillar IV) | 5000000 | 4950000 | 0.99 | 2022-08-01 | 2023-02-28 | Mwingi Central | -0.950, 38.055 | Completed | Ms. Lucy Ndunge
TCI-3 | Tharaka Honey Processing Equipment Supply | 14 | Aggregation & Industrial Parks (Pillar IV) | 9000000 | 8800000 | 0.978 | 2023-07-01 | 2024-12-31 | Kitui East | -1.200, 38.600 | Closed | Mr. Dan Munuve
EDU-1 | Construction of Mutomo Village Polytechnic | 11 | Skilled Human Capital (Pillar V) | 42000000 | 41800000 | 0.995 | 2022-04-01 | 2023-11-30 | Kitui South | -1.905, 38.250 | Closed | Arch. Kelvin Musembi
EDU-2 | Kyome ECD Classrooms Construction | 11 | Skilled Human Capital (Pillar V) | 18000000 | 18000000 | 1 | 2022-09-01 | 2024-08-31 | Mwingi West | -1.000, 37.750 | Completed | Ms. Lilian Wambua
EDU-3 | County Scholarship Disbursement FY 2024/25 | 11 | Skilled Human Capital (Pillar V) | 40000000 | 38500000 | 0.963 | 2024-09-01 | 2025-06-30 | Kitui Rural | -1.550, 37.700 | Initiated | Mr. Nicholas Muema
LHU-1 | Kitui Municipality Road Upgrading (Phase 1) | 22 | Physical Planning & Infrastructure | 150000000 | 50000000 | 0.333 | 2023-03-01 | 2026-06-30 | Kitui Central | -1.375, 38.020 | In Progress | Arch. Grace Nyamai
LHU-2 | Mwingi Land Adjudication and Survey | 22 | Physical Planning & Infrastructure | 25000000 | 24900000 | 0.996 | 2022-10-01 | 2023-12-31 | Mwingi North | -0.550, 38.350 | Completed | Mr. Titus Mutavi
LHU-3 | Kitui West Ward Administration Block | 22 | Physical Planning & Infrastructure | 45000000 | 5000000 | 0.111 | 2024-04-01 | 2025-05-30 | Kitui West | -1.450, 37.850 | Stalled | Eng. Joshua Musembi
RPT-1 | Kanziku-Kyamatu Road Gravelling | 18 | Infrastructure Development | 80000000 | 78000000 | 0.975 | 2022-06-01 | 2023-10-31 | Mwingi East | -0.600, 38.650 | Closed | Eng. Peninah Mbithe
RPT-2 | Kisasi-Tseikuru Road Culverts & Drifts | 18 | Infrastructure Development | 110000000 | 45000000 | 0.409 | 2024-03-01 | 2026-03-31 | Kitui Rural | -1.400, 37.900 | In Progress | Eng. David Nthuku
RPT-3 | Mutomo Sub-County Bridge Construction | 18 | Infrastructure Development | 35000000 | 0 | 0 | 2024-10-01 | 2025-12-31 | Mutomo (Kitui S.) | -1.850, 38.200 | Procurement | Mr. Stephen Ngungi
EEM-1 | Kitui East Climate Change Adaptation Project | 12 | Sustainable Resource Utilisation | 22000000 | 18000000 | 0.818 | 2023-04-01 | 2025-08-31 | Kitui East | -1.100, 38.700 | Delayed | Ms. Annastacia Wambua
EEM-2 | Mwingi North Street Lighting Installation | 12 | Sustainable Resource Utilisation | 15000000 | 15000000 | 1 | 2022-11-01 | 2023-06-30 | Mwingi North | -0.700, 38.500 | Completed | Mr. Simon Kasiva
EEM-3 | River Sand Harvesting Regulation Pilot | 12 | Sustainable Resource Utilisation | 7000000 | 540000 | 0.071 | 2024-08-01 | 2025-03-31 | Kitui West | -1.500, 37.750 | At Risk | Dr. Michael Kithome
FIN-1 | E-Revenue System Upgrade | 13 | Prudent Fiscal Management | 1500000 | 1500000 | 1 | 2023-09-01 | 2024-03-30 | County Wide | -1.365, 38.005 | Completed | Mr. Patrick Mumo
FIN-2 | County Budget Monitoring Framework Rollout | 13 | Prudent Fiscal Management | 3000000 | 1000000 | 0.333 | 2024-07-01 | 2025-06-30 | County Wide | -1.372, 38.008 | In Progress | Ms. Esther Koki
FIN-3 | Financial Management Software Procurement | 13 | Prudent Fiscal Management | 4000000 | 0 | 0 | 2024-11-01 | 2025-05-31 | County Wide | -1.360, 38.015 | Not Started | Mr. Nzioka Wambua
CGS-1 | Mutomo Sports Stadium Complex (Phase 1) | 15 | Social Development & Equity | 20000000 | 19500000 | 0.975 | 2022-05-01 | 2024-01-31 | Kitui South | -1.950, 38.350 | Closed | Ms. Winfred Mwende
CGS-2 | Mwingi Cultural Heritage Restoration | 15 | Social Development & Equity | 5000000 | 5000000 | 1 | 2023-11-01 | 2024-05-31 | Mwingi Central | -0.900, 38.100 | Completed | Mr. Nicholas Mwea
CGS-3 | Vulnerable Persons Empowerment Fund | 15 | Social Development & Equity | 10000000 | 2000000 | 0.2 | 2024-06-01 | 2025-09-30 | Mwingi West | -1.150, 37.600 | In Progress | Ms. Irene Kasiva
ICT-1 | County Digital Service Delivery Centres | 11 | Technological Advancement | 35000000 | 15000000 | 0.429 | 2023-01-01 | 2025-03-31 | Kitui Central | -1.378, 38.018 | Delayed | Mr. Kennedy Kitonga
ICT-2 | County Assembly Hansard System Implementation | 11 | Technological Advancement | 8000000 | 7900000 | 0.988 | 2022-10-01 | 2023-03-31 | Kitui Rural | -1.450, 37.950 | Completed | Ms. Florence Nthenya
ICT-3 | Mwingi East ICT Incubation Hub Setup | 11 | Technological Advancement | 1000000 | 0 | 0 | 2024-12-01 | 2025-06-30 | Mwingi East | -0.750, 38.500 | Procurement | Mr. Mutua King'oo