## schedule
Project | Phase | Milestone | Task | Timeframe
Elevated Steel Tank | 1. Mobilization & Site Prep. | 1.1 Project Launch | Site handover & official launch | May 26 - May 30, 2025 (5 days)
|  | 1.2 Site Setup | Mounting of project signposts | May 26 - May 27, 2025 (2 days)
|  | 1.3 Site Clearance | Mobilization & site clearance | May 28 - May 31, 2025 (4 days)
|  | 1.4 Temp. Structures | Erection of site house & demarcation | June 2 - June 6, 2025 (5 days)
|  | 1.5 Security | Perimeter fencing & main gate construction | June 9 - June 13, 2025 (5 days)
| 2. Foundation & Base | 2.1 Excavation | Excavation of tank foundation | June 16 - June 20, 2025 (5 days)
|  | 2.2 Base Construction | Setting up the base & curing | June 23 - June 27, 2025 (5 days)
|  | 2.3 Columns & Beams | Construction of columns & beams | June 30 - July 4, 2025 (5 days)
|  | 2.4 Foundation Curing | Curing for 21 days (July 7 - July 28) followed by 14 days curing (July 29 - August 11). NOTE: Project ends Aug 6 so this is not complete. | July 7 - August 6, 2025 (30 days)
| 3. Tower & Tank Erection | 3.1 Steel Tower | Supply and construction of the steel tower | June 30 - July 25, 2025 (4 weeks)
|  | 3.2 Tank Construction | Construction of tank and sealing joints | July 28 - August 1, 2025 (5 days)
| 4. Finishing & Commissioning | 4.1 Painting & Plumbing | Painting, plumbing, & automation | August 4 - August 6, 2025 (3 days)
|  | 4.2 Automation | Installation of all automation systems | August 4 - August 5, 2025 (2 days)
|  | 4.3 Final Fencing | Fencing around the tank | August 6, 2025 (1 day)
Borehole Solarization | 1. Reconditioning | 1.1 Pump Lifting | Lifting of pump from borehole | May 26 - May 28, 2025 (3 days)
|  | 1.2 Borehole Development | Flushing & developing the borehole | May 29 - May 30, 2025 (2 days)
|  | 1.3 Test Pumping | 24-hour test pumping | June 2 - June 3, 2025 (2 days)
|  | 1.4 New Pump Installation | Installation & test running of new pump | June 4 - June 6, 2025 (3 days)
|  | 1.5 Borehole Chamber | Construction of the borehole chamber | June 9 - June 13, 2025 (5 days)
| 2. Solarization | 2.1 Solar Structure | Siting & construction of solar structure | June 16 - June 20, 2025 (5 days)